## Test Report
Test Case ID | Date of Execution | Test | Defect ID | Additional comments
Result*
US1_1 | 2023-12-22 | Passed
US1_2 | 2023-12-22 | Passed | D1_2
US1_3 | 2023-12-22 | Passed | D1_3
US2_1 | 2023-12-22 | Passed
US2_2 | 2023-12-22 | Passed
US2_3 | 2023-12-22 | Failed | D2_1
US2_4 | 2023-12-22 | Passed | D2_2, D2_3
US2_5 | 2023-12-22 | Passed
US3_1 | 2023-12-22 | Passed | D3_1
US4_1 | 2023-12-22 | Passed
US4_2 | 2023-12-22 | Failed | D4_1
US5_1 | 2023-12-22 | Passed
US5_2 | 2023-12-22 | Passed

## US1
Test Case ID | US1_1 |  | Defect ID | D1_1
User Story Reference | US1 |  | Defect Title | Quantity_typo
Test Case Title | The products selected are included in the cart |  | Test Case ID
Test Case Description | When I select an item, it must be added to cart |  | Severity/Impact | Trivial
Prerequisite(s) | connected to network |  | Defect Detailed Description | At order summary, instead of quantity the website shows ''quantiry''
Test Step ID | Action | Excepted Result | Complementary Information
| Click ADD on a single product | Added to cart
Test Case ID | US1_2 |  | Defect ID | D1_2
User Story Reference | US1 |  | Defect Title | Negative amount of products
Test Case Title | Multiple products can be selected |  | Test Case ID | US1_2
Test Case Description | When I select multiple products, all of them must be added to cart |  | Severity/Impact | Major
Prerequisite(s) | connected to network |  | Defect Detailed Description | When I select multiple items, I can enter negative or null values, therefore quantity has negative value
Test Step ID | Action | Excepted Result | Complementary Information
| Click ADD on multiple products | All added to cart
Test Case ID | US1_3 |  | Defect ID | D1_3
User Story Reference | US1 |  | Defect Title | Negative total amount of money
Test Case Title | The amount of money are calculated automatically and corrected |  | Test Case ID | US1_3
Test Case Description | When I add items to cart, I want the total amount of money to be automatically calculated and correct |  | Severity/Impact | Major
Prerequisite(s) | connected to network |  | Defect Detailed Description | If I select items with negative values, their price is getting substracted from the total amount of money
Test Step ID | Action | Excepted Result | Complementary Information
| Add products to cart | Added to cart
| Proceed to Checkout | View summary of order and total price is the sum of all individual products
Test Case ID |  |  | Defect ID
User Story Reference |  |  | Defect Title
Test Case Title |  |  | Test Case ID
Test Case Description |  |  | Severity/Impact
Prerequisite(s) |  |  | Defect Detailed Description
Test Step ID | Action | Excepted Result | Complementary Information

## US2
Test Case ID | US2_1 |  | Defect ID | D2_1
User Story Reference | US2 |  | Defect Title | No country selected
Test Case Title | The order is correctly recorded |  | Test Case ID | US2_3
Test Case Description | When I proceed to checkout, the total amount of money and total number of items selected must be alligned with my order |  | Severity/Impact | Blocker
Prerequisite(s) | System must be connected to the network |  | Defect Detailed Description | I can proceed to complete an order without having selected a country to send the order
Test Step ID | Action | Excepted Result | Complementary Information
| After I have selected items, I press proceed to checkout | Total number of items is equal to the items I have selected and total amount of money is equal to the sum of its' item's price
Test Case ID | US2_2 |  | Defect ID | D2_2
User Story Reference | US2 |  | Defect Title | Unaccessible terms and conditions
Test Case Title | Place order |  | Test Case ID | US2-4
Test Case Description | When I place my order I want to be redirected to the next page to select the country I want to send the products |  | Severity/Impact | Minor
Prerequisite(s) | System must be connected to the network |  | Defect Detailed Description | When I click on the link of terms and conditions the page loading does not include them
Test Step ID | Action | Excepted Result | Complementary Information
| Click place order | Redirected to choose country
Test Case ID | US2_3 |  | Defect ID | D2_3
User Story Reference | US2 |  | Defect Title | Unable to return to order completion after viewing terms
Test Case Title | Select country |  | Test Case ID | US2_4
Test Case Description | When I have placed my order, I want to select the coyntry to ship my order |  | Severity/Impact | Minor
Prerequisite(s) | System must be connected to the network |  | Defect Detailed Description | When I enter the page to view the terms, I can't return back to my previous step and I can only be redirected to home page
Test Step ID | Action | Excepted Result | Complementary Information
| Select country | Country selected
Test Case ID | US2_4 |  | Defect ID
User Story Reference | US2 |  | Defect Title
Test Case Title | View and agree to the terms |  | Test Case ID
Test Case Description | When I have selected the country, I want to read and agree to the terms and conditions |  | Severity/Impact
Prerequisite(s) | System must be connected to the network |  | Defect Detailed Description
Test Step ID | Action | Excepted Result | Complementary Information
| Click on terms and conditions | Redirected to terms and conditions page
| Agree to the terms | Box checked
Test Case ID | US2_5
User Story Reference | US2
Test Case Title | Proceed to completion of order and see confirmation message
Test Case Description | After I have selected country and agreed on terms, I want to proceed to completion of order and see the confirmation message
Prerequisite(s) | System must be connected to the network
Test Step ID | Action | Excepted Result
| Click on proceed | View confirmation message

## US3
Test Case ID | US3_1 |  | Defect ID | US3_1
User Story Reference | US3 |  | Defect Title | Search bar has wrong name
Test Case Title | Search products |  | Test Case ID | US3_1
Test Case Description | When I type a product in search bar, I want the correct product to appear on my screen |  | Severity/Impact | Minor
Prerequisite(s) | System must be connected to the network |  | Defect Detailed Description | Search bar full name doesn’t appear before or after clicking it
Test Step ID | Action | Excepted Result | Complementary Information
| Click on search bar | Search bar open for typing
| Type the item I want to find | Item returned on my screen

## US4
Test Case ID | US4_1 |  | Defect ID | US4_1
User Story Reference | US4 |  | Defect Title | Unable to search top deals of other days
Test Case Title | View today's top deals |  | Test Case ID | US4_2
Test Case Description | When I click on top deals button I want to view today's top deals |  | Severity/Impact | Major
Prerequisite(s) | System must be connected to the network |  | Defect Detailed Description | When I change the date, the top deals remain the same
Test Step ID | Action | Excepted Result | Complementary Information
| Click on Top Deals Button | Redirected to top deals page where they are displayed
Test Case ID | US4_2
User Story Reference | US4
Test Case Title | View top deals of previous or future days
Test Case Description | When I click on top deals button and I enter a specific date I want to view its' own top deals
Prerequisite(s) | System must be connected to the network
Test Step ID | Action | Excepted Result
| Click on Top Deals Button | Redirected to top deals page where they are displayed
| Select a date | View the top deals of that day

## US5
Test Case ID | US5_1 |  | Defect ID
User Story Reference | US5 |  | Defect Title
Test Case Title | Use valid promo code |  | Test Case ID
Test Case Description | As a user I want to use Promo Code for the order I have in the cart |  | Severity/Impact
Prerequisite(s) | System must be connected to the network |  | Defect Detailed Description
Test Step ID | Action | Excepted Result | Complementary Information
| Insert a valid promo code | Discount is displayed
Test Case ID | US5_2
User Story Reference | US5
Test Case Title | Use invalid promo code
Test Case Description | When I use an invalid promo code, I want to see a message stating that my code is invalid and no discount has been added
Prerequisite(s) | System must be connected to the network
Test Step ID | Action | Excepted Result
| Insert an invalid promo code | Invalid discount message displayed and no discount added